## Customer Test Plan
TEST PLAN (This section needs to be completed before your Tests) |  |  |  |  | TEST LOG (This section is to be completed after each of your Tests)
Test Number | Test Preconditions/Prerequisites | Test Description | Expected Results | Test Data | Actual Results | Actual Results match Expected? (Yes/No) | Comments / Corrective Action Required
1 | Customer account is registered with these credentials: Email - customer1@mail.com Password- Pass@word1 | Testing Sign In of a registered customer, with correct credentials | Customer is successfully signed in, notification is briefly displayed, customer name is displayed in the navbar, customer account link is visible, logout link is visible | Customer sign in page - email entered is customer1@mail.com with password Pass@word1
2 | Customer account is registered with these credentials: Email - customer1@mail.com Password- Pass@word1 | Testing Sign In of a registered customer, with correct email, incorrect password | Error message is displayed - Email or password is incorrect | Customer sign in page - email entered is customer1@mail.com with password B@dPassword1
3 | Customer account is registered with these credentials: Email - customer1@mail.com Password- Pass@word1 | Testing Sign In of a registered customer, with incorrect email, correct password | Error message is displayed - Email or password is incorrect | Customer sign in page - email entered is no1customer@mail.com with password Pass@word1
4 | Customer account is registered with these credentials: Email - customer1@mail.com Password- Pass@word1 | Testing Sign In of a registered customer, with incorrect email, incorrect password | Error message is displayed - Email or password is incorrect | Customer sign in page - email entered is someone@mail.com with password noPassword@2
5 | Customer is Signed In | Testing Logout of a Signed In Customer | Notification is displayed - Succesfully signed out. Sign In and Signup links are visible in the navbar, no access to a customer account page | Navbar - Logout link clicked
6 | Customer is not currently registered | Sign Up of a new Customer | Account is created - Customer is able to Sign In | Data to be entered on the Signup page - First Name - Joe, Last Name - Doe, Email address - john_doe@mail.com, Password - Pass@word1, Confirm Password - Pass@word1, Click signup - notification is displayed with a link to activation email, open email, click on the activation link, notification is displayed confirming activation of the email, go to sign in page and sign in with credentials used to sign up
7 | Customer is signed in | Customer adds new delivery address | Delivery address is added and displayed on your addresses page | Page Account -> Your addresses -> Add Address link -> Enter Name -John Doe Street address - Flat 8b London road 22 City/Town - London Post Code - L23 W2A
8 | Customer is signed in | Customer edits Login & Security details - Email | Email is updated | Page Account -> Login & Security -> Press Edit on email row -> enter new email -> press Update
9 | Customer is signed in | Customer edits Login & Security details - Name | Name is updated | Page Account -> Login & Security -> Press Edit on email row -> enter new name -> press Update
10 | Customer is singed in | Customer edits Login & Security details - Phone number | Phone number is updated | Page Account -> Login & Security -> Press Edit on email row -> enter new phone number -> press Update
11
12
13
14
15
16

## Administrator Test Plan
TEST PLAN (This section needs to be completed before your Tests) |  |  |  |  | TEST LOG (This section is to be completed after each of your Tests)
Test Number | Test Preconditions/Prerequisites | Test Description | Expected Results | Test Data | Actual Results | Actual Results match Expected? (Yes/No) | Comments / Corrective Action Required
1 | Administrator account is present with these credentials: Email - admin@mail.com Password- Pass@word1 | Testing Administrator Sign In, with correct credentials | Administrator is successfully signed in and redirected to dashboard. | Administrator sign in page - credentials entered: Email - admin@mail.com Password- Pass@word1
2 | Administrator account is present with these credentials: Email - admin@mail.com Password- Pass@word1 | Testing Administrator Sign In, with correct email, incorrect password | Error message is displayed - Email or password is incorrect | Administrator sign in page - credentials entered: Email - admin@mail.com Password- Pass@word123
3 | Administrator account is present with these credentials: Email - admin@mail.com Password- Pass@word1 | Testing Administrator Sign In, with incorrect email, correct password | Error message is displayed - Email or password is incorrect | Administrator sign in page - credentials entered: Email - administrator@mail.com Password- Pass@word1
4 | Administrator account is present with these credentials: Email - admin@mail.com Password- Pass@word1 | Testing Administrator Sign In, with incorrect email, incorrect password | Error message is displayed - Email or password is incorrect | Administrator sign in page - credentials entered: Email - administrator@mail.com Password- Pass@word12345
5 | Administrator is Signed In | Testing Logout of a Signed In Administator | Administrator is signed out and redirected to login page | Navbar - Logout link clicked
6 | Administrator is Signed In | Testing adding new employee | Employee is added to the list, Newly added employee is able to use/sign into Warehouse application | Page Add new Employee -> values entered ( * Id is autogenerated) First name : Jack, Last Name: Sparrow, Password: P@ssword1, Confirm Password: P@ssword1, Tasks selected: all, -> Press Add Employee
7 | Administrator is Signed In - employee is present, Name: Jack Black, Current Password: P@ssword1 | Testing changing employee password | Employee password is chaged, Employee is able to sign into warehouse application with a new password, old password is invalid | View all employees page -> Select employee Jack Black -> Press Edit -> Press Reset Password -> Enter Password: newP@ssword1 , Confirm Password: newP@ssword1 -> Press Update Password
8 | Administrator is Signed In | Add new Item to the catalog | Item is added to the catalog with corresponding details -> Item Title: Bose B5 Speakers, Item Description: Awesome Speakers blablabla, Price: 499.00, Category: Speakers, ImageURI: bose-b5-speakers.png | Add new item page -> Enter following Details Item Title: Bose B5 Speakers, Item Description: Awesome Speakers blablabla, Price: 499.00, Category: Speakers, ImageURI: bose-b5-speakers.png -> press Add Item
9
10

## Employee Test Plan
TEST PLAN (This section needs to be completed before your Tests) |  |  |  |  | TEST LOG (This section is to be completed after each of your Tests)
Test Number | Test Preconditions/Prerequisites | Test Description | Expected Results | Test Data | Actual Results | Actual Results match Expected? (Yes/No) | Comments / Corrective Action Required
1 | Employee account is present with these credentials: Username - 9002990 Password- Pass@word1 | Testing Employee Sign In, with correct credentials | Administrator is successfully signed in and redirected to dashboard. | Employee sign in form - credentials entered: Username - 9002990 Password- Pass@word1
2 | Employee account is present with these credentials: Username - 9002990 Password- Pass@word1 | Testing Employee Sign In, with correct username, incorrect password | Error message is displayed - Email or password is incorrect | Employee sign in form - credentials entered: Username - 9002990 Password- Pass@word1123
3 | Employee account is present with these credentials: Username - 9002990 Password- Pass@word1 | Testing Employee Sign In, with incorrect username, correct password | Error message is displayed - Email or password is incorrect | Employee sign in form - credentials entered: Username - 1102990 Password- Pass@word1
4 | Employee account is present with these credentials: Username - 9002990 Password- Pass@word1 | Testing Employee Sign In, with incorrect username, incorrect password | Error message is displayed - Email or password is incorrect | Employee sign in form - credentials entered: Username - 2202990 Password- Pass@word1332
5 | Employee is Signed In | Testing Logout of a Signed In employee | Employee is signed out and Sign In form is shown | Main form - click logout button
6
7
8
9
10